## Jira
Issue id | Summary | Issue key | Issue Type | Status | Project type | Project lead | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Last Viewed | Resolved | Due date | Description | Environment | Watchers | Watchers Id | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Œ£ Original Estimate | Œ£ Remaining Estimate | Œ£ Time Spent | Security Level | Custom field (Deadline) | Custom field (Development) | Custom field (Issue color) | Custom field (Rank) | Parent summary | Status Category
10062 | chat BE | CS300G01-63 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2023-01-08 16:54 | 2023-01-08 16:55 | 2023-01-08 16:55 | 2023-01-08 16:55 | 2022-12-22 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005h:09 | Sprint 03 | Done
10061 | merge code | CS300G01-62 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2023-01-08 16:51 | 2023-01-08 16:52 | 2023-01-08 17:10 | 2023-01-08 16:51 | 2023-01-09 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005h:0i | Sprint 05 | Done
10060 | test plan | CS300G01-61 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2023-01-08 16:50 | 2023-01-08 16:52 | 2023-01-08 17:10 | 2023-01-08 16:50 | 2023-01-08 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005h:1 | Sprint 05 | Done
10054 | create tips admin | CS300G01-55 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-25 20:20 | 2023-01-08 16:53 | 2023-01-08 16:53 | 2022-12-27 13:27 | 2022-12-28 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005k:i | Sprint 04 | Done
10053 | booking insight admin | CS300G01-54 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-25 18:46 | 2023-01-08 16:50 | 2023-01-08 17:10 | 2023-01-08 16:50 | 2022-12-28 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005h:i | Sprint 05 | Done
10052 | detail accommodation view | CS300G01-53 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-25 18:43 | 2022-12-27 13:27 | 2023-01-08 17:10 | 2022-12-27 13:27 | 2022-12-30 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005k: | Sprint 05 | Done
10050 | Wishlist | CS300G01-51 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Le Gia Khanh | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-09 21:39 | 2023-01-08 16:53 | 2023-01-08 16:53 | 2023-01-05 21:35 | 2022-12-17 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005l: | Sprint 04 | Done
10049 | Setting UI | CS300G01-50 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-03 15:47 | 2022-12-17 21:33 | 2023-01-08 17:10 | 2022-12-17 21:33 | 2022-12-04 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005j: | Sprint 03 | Done
10048 | Homepage UI | CS300G01-49 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-03 15:45 | 2022-12-03 15:46 | 2023-01-08 17:10 | 2022-12-03 15:46 | 2022-12-03 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i00054:ud | Sprint 03 | Done
10047 | Wishlist UI | CS300G01-48 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Le Gia Khanh | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-12-02 18:14 | 2022-12-05 19:49 | 2023-01-08 17:10 | 2022-12-05 19:49 | 2022-12-04 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0005d: | Sprint 03 | Done
10046 | Registration UI | CS300G01-47 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-11 22:41 | 2022-11-22 10:57 | 2022-11-11 22:47 | 2022-11-22 10:57 | 2022-11-19 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-18 | {} |  | 0¦i0002x:i | Sprint 02 | Done
10045 | Profile UI | CS300G01-46 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-11 22:41 | 2022-12-02 18:13 | 2022-12-02 18:13 | 2022-12-02 18:13 | 2022-11-19 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-19 | {} |  | 0¦i0002w: | Sprint 02 | Done
10044 | Notification/Chat UI | CS300G01-45 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Linh Nguyen Ha Ngoc | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-11 22:40 | 2022-12-25 14:25 | 2022-12-03 15:45 | 2022-12-25 14:25 | 2022-11-23 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-19 | {} |  | 0¦i00032:i | Sprint 02 | Done
10040 | facebook connect | CS300G01-41 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Le Gia Khanh | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 21:04 | 2022-12-02 18:45 | 2022-11-11 22:47 | 2022-12-02 18:45 | 2022-11-26 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-25 | {} |  | 0¦i00054:o | Sprint 02 | Done
10039 | feature setting | CS300G01-40 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Linh Nguyen Ha Ngoc | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 21:04 | 2023-01-08 16:52 | 2022-12-25 20:48 | 2023-01-08 16:50 | 2022-11-26 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-20 | {} |  | 0¦i0005h:9 | Sprint 05 | Done
10037 | chat | CS300G01-38 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 21:04 | 2023-01-08 16:50 | 2022-12-09 21:32 | 2023-01-08 16:50 | 2022-11-27 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-25 | {} |  | 0¦i0005h:2 | Sprint 02 | Done
10036 | basic book | CS300G01-37 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 21:04 | 2022-12-17 21:20 | 2022-12-09 21:31 | 2022-12-17 21:20 | 2022-12-10 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-19 | {} |  | 0¦i0005h: | Sprint 02 | Done
10035 | categorize accommodation | CS300G01-36 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 20:55 | 2022-11-27 20:46 | 2022-11-11 22:45 | 2022-11-27 20:46 | 2022-11-25 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-20 | {} |  | 0¦i00054:or | Sprint 02 | Done
10034 | filter and sort result | CS300G01-35 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 20:53 | 2022-11-27 20:36 | 2022-11-11 22:46 | 2022-11-27 20:36 | 2022-11-25 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-25 | {} |  | 0¦i0002x:9 | Sprint 02 | Done
10033 | search house | CS300G01-34 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 20:53 | 2022-12-03 21:21 | 2022-11-11 22:46 | 2022-12-03 21:21 | 2022-11-22 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-23 | {} |  | 0¦i00030: | Sprint 02 | Done
10031 | renter and host profile setting | CS300G01-32 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 20:50 | 2022-12-25 20:04 | 2022-11-11 22:44 | 2022-12-25 20:04 | 2022-11-18 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-19 | {} |  | 0¦i0005i: | Sprint 02 | Done
10030 | Host create listing | CS300G01-31 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-10 20:47 | 2023-01-08 16:50 | 2022-12-02 18:30 | 2023-01-08 16:50 | 2022-12-04 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-25 | {} |  | 0¦i0005h:4 | Sprint 02 | Done
10029 | Signup/Signin | CS300G01-30 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-05 20:40 | 2022-11-10 20:39 | 2022-11-05 20:41 | 2022-11-10 20:39 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001g: | Sprint 03 | Done
10027 | Section 2, 3, 5 | CS300G01-28 | Subtask | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | tttvy20 | tttvy20 | 2022-11-04 10:10 | 2022-11-04 10:10 | 2023-01-08 17:10 | 2022-11-04 10:10 |  |  |  | tttvy20 | 6347734b5efe6ce125d8706a | [9 empty] | {} |  | 0¦i00053: | Vision document | Done
10026 | Section 1, 3 | CS300G01-27 | Subtask | Done | software | Quynh Le Pham Nhat | Medium | Done | Le Gia Khanh | tttvy20 | tttvy20 | 2022-11-04 10:09 | 2022-11-04 10:09 | 2023-01-08 17:10 | 2022-11-04 10:09 |  |  |  | tttvy20 | 6347734b5efe6ce125d8706a | [9 empty] | {} |  | 0¦i0004v: | Vision document | Done
10025 | Section 4, 6 | CS300G01-26 | Subtask | Done | software | Quynh Le Pham Nhat | Medium | Done | Linh Nguyen Ha Ngoc | tttvy20 | tttvy20 | 2022-11-04 10:09 | 2022-11-04 10:09 | 2023-01-08 17:10 | 2022-11-04 10:09 |  |  |  | tttvy20 | 6347734b5efe6ce125d8706a | [9 empty] | {} |  | 0¦i0004n: | Vision document | Done
10024 | Assign map and location (map page for place) | CS300G01-25 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 16:49 | 2022-11-11 02:24 | 2022-11-03 16:49 | 2022-11-11 02:24 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i00019: | Sprint 01 | Done
10020 | Add information and constructor for classes | CS300G01-21 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Linh Nguyen Ha Ngoc | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 16:45 | 2022-11-10 20:39 | 2022-11-03 16:46 | 2022-11-10 20:39 |  | Based on App Structure.doc |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001h: | Sprint 01 | Done
10019 | Create oop structure and file structure | CS300G01-20 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 16:44 | 2022-11-05 20:10 | 2023-01-08 17:10 | 2022-11-05 20:10 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0002d: | Sprint 01 | Done
10018 | Add tips page for host | CS300G01-19 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Le Gia Khanh | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 16:44 | 2022-12-03 20:56 | 2022-11-11 22:52 | 2022-12-03 20:56 | 2022-11-25 |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [8 empty] | 2022-11-25 | {} |  | 0¦i00033: | Sprint 01 | Done
10017 | Navigation bar for renter, host, admin | CS300G01-18 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 16:43 | 2022-11-05 10:07 | 2022-11-03 16:46 | 2022-11-05 10:07 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0002v: | Sprint 01 | Done
10016 | Create firebase data | CS300G01-17 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 16:41 | 2022-11-05 15:31 | 2022-11-03 16:41 | 2022-11-05 15:31 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0002b: | Sprint 01 | Done
10014 | Collect data for host/user/photo and help | CS300G01-15 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Linh Nguyen Ha Ngoc | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 12:44 | 2022-11-06 23:28 | 2022-11-03 12:44 | 2022-11-06 23:28 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i00027: | Sprint 00 | Done
10013 | Host structure | CS300G01-14 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 08:03 | 2022-11-03 12:44 | 2022-11-03 12:44 | 2022-11-03 12:44 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001x: | Sprint 00 | Done
10012 | User structure | CS300G01-13 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 08:03 | 2022-11-03 08:03 | 2022-11-03 08:03 | 2022-11-03 08:03 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001f: | Sprint 00 | Done
10011 | Admin structure | CS300G01-12 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | blgcat20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 07:59 | 2022-11-03 12:43 | 2022-11-03 12:43 | 2022-11-03 12:43 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001v: | Sprint 00 | Done
10010 | Visual key | CS300G01-11 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Le Gia Khanh | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 07:58 | 2022-11-11 02:59 | 2022-11-03 07:58 | 2022-11-11 02:59 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001z: | Sprint 00 | Done
10009 | UI design renter | CS300G01-10 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 07:55 | 2022-11-03 11:04 | 2022-11-03 07:56 | 2022-11-03 11:04 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001r: | Sprint 00 | Done
10008 | Vision document | CS300G01-9 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | tttvy20 | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-11-03 07:54 | 2022-11-04 10:07 | 2022-11-03 07:57 | 2022-11-04 10:07 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001j: | Sprint 01 | Done
10007 | Project proposal | CS300G01-8 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-10-22 20:45 | 2022-10-22 20:46 | 2022-10-22 20:46 | 2022-10-22 20:46 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i0001b: | Sprint 00 | Done
10000 | Create master plan for the app | CS300G01-1 | Task | Done | software | Quynh Le Pham Nhat | Medium | Done | Quynh Le Pham Nhat | Quynh Le Pham Nhat | Quynh Le Pham Nhat | 2022-10-18 23:48 | 2022-11-05 20:09 | 2022-11-03 07:57 | 2022-11-05 20:09 |  |  |  | Quynh Le Pham Nhat | 6347671ecafc998a91cf88d4 | [9 empty] | {} |  | 0¦i00017: | Sprint 01 | Done